## Pre-Production Checklist
PRE-PRODUCTION CHECKLIST | Y / N | NOTES
CONCEPT
Is initial game concept defined? | Y
Are platform and genre specified? | Y
Is mission statement completed? | Y
Are basic game play elements defined? | Y
Is prototype completed? | N
Is risk analysis completed? | Y
Is the concept pitch ready for approval? | Y
GAME REQUIREMENTS
Are "must have," "want to have," and "nice to have" features defined? | N
Are constraints defined and accounted for in feature sets? | Y
Are milestones and deliverables defined? | Y
Has technology been evaluated against the desired feature set? | Y
Are tools and pipeline defined? | Y
Is basic design documentation completed? | Y
Is basic technical documentation completed? | N
Is risk analysis completed? | Y
GAME PLAN
Is budget completed? | N/A
Is initial schedule completed? | Y
Is initial staffing plan completed? | N/A
Have core team members approved the schedule and staffing plan? | Y

## Prototype
PHASE 1 CHECKLIST | Y / N | NOTES
Board game implementation
Player Character
Melee weapon
Ranged weapon
Camera Movement
Panning
Collision
Trigger interaction
Environment Mechanics
objects in fore/mid/background
Player character sprite height
Lighting
Enemies
tracking AI
collision
Pathing
Trigger interaction
Sound
Basic sound que
1 music track
1 ambient soundtrack
Graphics
Ques
Animations and sprites
Several static objcts
Several physics interactive objects
UI
Health
Debugging values (combat)
Status effects
Map
Screen Effects
Triggered distortion
local distortions
Particle Effects
smoke
explosive
weapon output

## Production Checklist
PRODUCTION CHECKLIST | Y / N | NOTES
PLAN IMPLEMENTATION
Is game plan clearly communicated to team? | Y
Is game plan in publically accessible place? | Y | github
qw | Y
Does everyone on team have the necessary resources to do their work? | Y | Unity, photoshop, Krita
Is process in place for controlling feature creep? | Y | GDD
Is process in place for managing task dependencies? | N
PROGRESS TRACKING
Is there a game plan to track progress against? | Y
Is process in place for producer to track all task progress? | Y | google doc spreadsheet
Is progress posted in visible location? | Y | posted on shared google doc
TASK COMPLETION
Does each task have clearly defined exit criteria? | Y | all tasks defined by competion
Are these exit criteria publicly available to the team? | Y

## Testing Checklist
TESTING CHECKLIST | Y / N | NOTES
VALIDATE PLAN
Is test plan written? | Y
Is game plan updated for QA? | N
Has test plan been updated with any changes to the game plan? | N
Are testing milestones accounted for in the schedule? | N
Is bug-tracking software available for the testers and development team? | N
Are all areas of the game tested? | N
Are all bugs regressed and closed? | N
CODE RELEASE
Has development team submitted a final code release candidate? | N
Is there ample time in the schedule for QA to complete the test plan on the code release candidate? | N
Has QA approved the product for code release? | N
CONSOLE ONLY: Has code released game been submitted to console manufacturer for approval? | N
CONSOLE ONLY: Has console manufacturer approved game for final replication? | N

## Wrap-up Checklist
WRAP UP CHECKLIST | Y / N | NOTES
ARCHIVE PLAN
Is closing kit completed? | N
LEARN FROM EXPERIENCE
Is post mortem completed? | N
Is post mortem published to the entire development studio? | N